جامعة المنوفية

كلية الحاسبات والمعلومات

2026-2027

Menofyia University

System Analysis & design Project

second year

2026-2027

| No. | Name | Section |
| --- | --- | --- |
| 1202540938 | Marwa Magdy Ibrahim Mohamed | 1 |
| 1202540684 | Sara Samir Mohamed Omara | 1 |
| 1202540943 | Mariam Mostafa Taha Elnemr | 1 |
| 1202540380 | Mariam Mohamed Abdelwahed Elkhrakhisy | 1 |
| 1202540071 | Omnia Adel Mohamed Elsayad | 1 |

Planning (Project Plan)

Project Identification

Project Name:

Student Grading & Rubrics System

Current Problem:

- Unequal and inconsistent grading: Different instructors or teaching assistants often grade differently for the same assignment because there are no clear, shared rubrics to follow.

- Wasting too much time: Teachers spend a huge amount of time manually evaluating each student, summing up scores, and writing down feedback..

- Students don't understand their grades: Students usually just get a final mark without knowing where they lost points or what criteria were used, which leads to confusion and lots of questions.

- Human errors in calculation: Transferring grades manually from papers to spreadsheets often causes calculation or typing errors.

Description about project:

- The system can simplify and speed up the grading process for assignments and projects by using custom rubrics. It enables the instructor to create detailed criteria for any task and evaluate students online. The system works to calculate final grades automatically without any calculation errors and saves a lot of time for teachers. It enables the student to see his full grade breakdown and detailed feedback clearly on his account. The system can store all student grades safely in a database to prevent them from being lost, and it generates final reports for the department easily with less effort.

System Request

| System Request— Student Grading & Rubrics System |  |
| --- | --- |
| Project Sponsor: | Eng. Eman (Head of Information System Department) |
| Business Need: | - Stop unfair and different grading between teaching assistants. - Save time spent on manual grade calculations and paperwork. - Make students understand their grades clearly and avoid complaints. - Keep all student records safe from loss. |
| Business Requirements: | - User login system with different roles (Admin, Instructor, Student). - Create custom rubrics for assignments and projects. - Online grading and evaluation page. 4- Automatic calculation for final grades. |
| Business Value: | - Providing clear and accurate feedback to students. - Saving time and effort for instructors. - aving cost by removing paper records. - Saving grading consistency and fairness |
| Special Issues or Constraints: | - Deadline by the end of the semester. - High security to protect students' grade data. |

Feasibility Analysis

Technical Feasibility

  - We need to design the system using HTML, CSS, and JavaScript for the frontend interface.

  - We need backend languages like Node.js or Python to handle the logic and database connections.

  - We need a reliable database (like MySQL) to securely store student grades and rubrics.

  - We need to make this website to work on an specialized operating system like windows or android

Economic Feasibility

- The development cost will be very low since we are using open-source tools and standard university computers.

- Any potential loss or risk will be minimal, mainly related to minor server issues that can be easily fixed.

- The economic benefits (saving time, reducing paperwork, and improving grading accuracy) are much higher than the setup costs.

Organizational Feasibility

- Management prowess:The initial project team has the necessary technical skills and software engineering knowledge to plan, design, and manage the system successfully.

- Resource sufficiency: The required nonfinancial resources are available, including:

- Human resources: Developers (students) and the supervising instructor

- Facilities & Equipment: Laptops, personal computers, and internet access.

- Software tools: Free, open-source development tools and database management systems

Time Estimation

|  | Planning | Analysis | Design | Implementation |
| --- | --- | --- | --- | --- |
| Standard percentages | 15% | 20% | 35% | 30% |
| Estimated time based on planning time | Actual: 11 days | 16 days | 25 days | 22 days |

Tasks Identification

| System Request | Name of Task |
| --- | --- |
| 9/11/2026 | Start Date |
| 12/11/2026 | End Date |
| Marwa,Sara | Person assigned to task |
| High | Priority |
| Microsoft word | Resources Needed |
| 4 hours | Estimated Time |
| 2hours | Actual Time |

| Feasibility Study | Name of Task |
| --- | --- |
| 12/11/2026 | Start Date |
| 17/11/2026 | End Date |
| Mariam,Mariam | Person assigned to task |
| High | Priority |
| Microsoft word | Resources Needed |
| 8 hours | Estimated Time |
| 5 hours | Actual Time |

| Pert Chart, Grantt Chart | Name of Task |
| --- | --- |
| 17/11/2026 | Start Date |
| 19/11/2026 | End Date |
| Omnia,Marwa | Person assigned to task |
| High | Priority |
| Ms project,Time Estimates | Resources Needed |
| 9 hours | Estimated Time |
| 6 hours | Actual Time |

| Interview | Name of Task |
| --- | --- |
| 19/11/2026 | Start Date |
| 24/11/2026 | End Date |
| Sara,Mariam | Person assigned to task |
| Medium | Priority |
| Microsoft word | Resources Needed |
| 16 hours | Estimated Time |
| 14 hours | Actual Time |

| Questionnaire | Name of Task |
| --- | --- |
| 19/11/2026 | Start Date |
| 23/11/2026 | End Date |
| Mariam,Omnia | Person assigned to task |
| medium | Priority |
| Form drive | Resources Needed |
| 5 hours | Estimated Time |
| 2 hours | Actual Time |

| Data Flow Diagram | Name of Task |
| --- | --- |
| 24/11/2026 | Start Date |
| 29/11/2026 | End Date |
| Marwa,Sara | Person assigned to task |
| High | Priority |
| Internet | Resources Needed |
| 1 day | Estimated Time |
| 18 hours | Actual Time |

| Data Store | Name of Task |
| --- | --- |
| 29/11/2026 | Start Date |
| 2/12/2026 | End Date |
| Mariam,Mariam | Person assigned to task |
| High | Priority |
| Microsoft word | Resources Needed |
| 1 day | Estimated Time |
| 17 hours | Actual Time |

| process specification | Name of Task |
| --- | --- |
| 29/11/2026 | Start Date |
| 3/12/2026 | End Date |
| Omnia,Marwa | Person assigned to task |
| High | Priority |
| Microsoft word | Resources Needed |
| 1 day and 10 hours | Estimated Time |
| 19 hours | Actual Time |

| Entity Relationship | Name of Task |
| --- | --- |
| 2/12/2026 | Start Date |
| 6/12/2026 | End Date |
| Sara,Mariam | Person assigned to task |
| High | Priority |
| StarUML | Resources Needed |
| 1 day and 10 hours | Estimated Time |
| 19 hours | Actual Time |

| Normalization | Name of Task |
| --- | --- |
| 2/12/2026 | Start Date |
| 6/12/2026 | End Date |
| Mariam,Omnia | Person assigned to task |
| High | Priority |
| StarUML | Resources Needed |
| 1 day and 10 hours | Estimated Time |
| 19 hours | Actual Time |

| design | Name of Task |
| --- | --- |
| 7/12/2026 | Start Date |
| 2/1/2027 | End Date |
| Marwa,Sara,Mariam,Mariam,Omnia | Person assigned to task |
| High | Priority |
| Visual studio code | Resources Needed |
| 18 days | Estimated Time |
| 13 days | Actual Time |

| Implementation | Name of Task |
| --- | --- |
| 2/1/2027 | Start Date |
| 24/1/2027 | End Date |
| Marwa,Sara,Mariam | Person assigned to task |
| High | Priority |
| Visual studio code | Resources Needed |
| 16 days | Estimated Time |
| 11 days | Actual Time |

Pert Chart (MS-Project_Time Estimates)

Gantt chart (MS-Project_Time Estimates)